## Gantt Chart - Manual Duration
Task Name | Assigned to | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete
Understading the problem | Everyone | 2018-04-15 | 2018-04-19 | 4 | 4 | 0 | 100%
Collecting information about the existing infrastructure | Everyone | 2018-04-19 | 2018-04-21 | 2 | 2 | 0 | 100%
Proposing the solutions | Individual ideas | 2018-04-21 | 2018-04-28 | 7 | 7 | 0 | 100%
Documentation. | Mehul Warade & Omar Alturkistani | 2018-04-15 | 2018-05-10 | 25 | 7.5 | 17.5 | 30%
Selection of the best solution. | Everyone | 2018-04-28 | 2018-04-29 | 1 | 1 | 0 | 100%
2D overview of our design. | Prudhvi Raj Ayyappan | 2018-04-28 | 2018-05-08 | 10 | 10 | 0 | 100%
Collection of Data from users. | Mehul Warade | 2018-04-28 | 2018-05-01 | 3 | 3 | 0 | 100%
3D CAD model of the design. | John Amgad Abadir Riad | 2018-04-25 | 2018-05-05 | 10 | 10 | 0 | 100%
Documentation. | Mehul Warade & Omar Alturkistani | 2018-04-15 | 2018-05-10 | 25 | 12.5 | 12.5 | 50%
DfX principals: Development and Production Phase. | Prudhvi Raj Ayyappan | 2018-05-08 | 2018-05-10 | 2 | 2 | 0 | 100%
DfX principals: Utilization and Disposal Phase. | Nathan Wong | 2018-04-28 | 2018-05-02 | 4 | 4 | 0 | 100%
Documentation. | Mehul Warade & Omar Alturkistani | 2018-04-15 | 2018-05-10 | 25 | 17.5 | 7.5 | 70%
Collection of Images for documentation. | Nathan Wong | 2018-05-02 | 2018-05-07 | 5 | 5 | 0 | 100%
Getting reviews on our proposed design from tutors. | Everyone | 2018-05-01 | 2018-05-05 | 4 | 4 | 0 | 100%
Documentation. | Mehul Warade & Omar Alturkistani | 2018-04-15 | 2018-05-10 | 25 | 25 | 0 | 100%
Final Documentation and Proof-reading. | Mehul Warade. | 2018-05-10 | 2018-05-12 | 2 | 2 | 0 | 100%
Gantt Chart. | Mehul Warade | 2018-05-12 | 2018-05-13 | 1 | 1 | 0 | 100%
Formulas:
End Date = IF(ISBLANK([Duration (Days)]),"",[Duration (Days)]+[Start Date])